## QA Report Summary
Module / Category | Type | Description | Still Proble Persist After Migration | Action Required | Status
001 - Chart Window | Bug | Except for BNF Futures, selected charts do not load immediately. The user must close and reopen the chart to view the selection.+1 | Yes | Need to Fix | Resolved
001 - Chart Window | Bug | The countdown timer is not synced with the original TradingView candle timer. | Yes | Need to Fix | Resolved
001 - Chart Window | Bug | The indicator toggle is not working. | Yes | Need to Fix | Resolved
001 - Chart Window | Working | Time frame switching is working well. | Yes | No Problem | Resolved
002 - Balance & P&L | Bug | Balance and P&L have an issue related to the "positions tab".+1 | Yes | Need to Fix | Resolved
002 - Balance & P&L | Blocker | Unable to check balance validation due to the display issue.+1 | No | No Problem | Resolved
003 - Profile Page | Bug | The profile page needs optimization; some data is cut off at the bottom of the screen. | Yes | Need to Fix | Not Resolved
003 - Profile Page | Note | Login & Logout button was tested/mentioned. | Yes | No Problem | Resolved
004 - Place Order | Bug | Pulling lot size is malfunctioning; it sometimes pulls the BNF lot size for other symbols. | No | No Problem | Resolved
004 - Place Order | Bug | On page refresh, it incorrectly redirects to the default "BNF futures" page instead of remaining on the previous page. | Yes | Need to Fix | Partial Resolved
004 - Place Order | Bug | Placed orders do not update immediately in the positions tab. It sometimes updates with a delay or only after placing another order.+1 | Yes | Need in Fix | Resolved
004 - Place Order | Bug | Orders update immediately in the "Orders" tab, but not in the "positions" tab. | Yes | Need to Fix | Resolved
004 - Place Order | Bug | Limit orders show an "Invalid limit price" message if the limit buy price is higher than the current price (and vice versa). | Yes | Need to Fix | Resolved
004 - Place Order | Bug | Major order placement issue: a random delay occurs before the "previous order filled" message appears and the position is shown. | Yes | Need to Fix | Resolved
004 - Place Order | Bug | The "Margin ReQ" information being pulled is wrong. | Yes | Need to Fix | Partial Resolved
004 - Place Order | Bug | Quantity mismatch: selecting 120 Qty places an order for 90; selecting 60 places an order for 30. | Yes | Need to Fix | Resolved
004 - Place Order | Requirement | The current price should be displayed beside the Instrument Name. | Need this | Need to Fix | Resolved | Issue
004 - Place Order | Requirement | A Market depth window is needed for limit order price assumptions. | Need this | Need to Fix | Not Resolved | Failing to load
004 - Place Order | Requirement | The app needs to show the approximate charges. | Need this | Need to Fix | Resolved
004 - Place Order | Requirement | Place order and positions should be in the same window, like a dropdown. | Need this | Need to Fix | Resolved | Not Properly Placed
004 - Place Order | Note | SL-Market orders are not required currently; will implement in the future if needed.+1 | Yes | Need to Fix | Resolved
005 - Bottom Tabs | Critical Bug | Complete malfunction of the place order, positions, orders & trades functions. | Yes | Need to Fix | Resolved
005 - Bottom Tabs | Bug | Option chain live data is not updating for strike prices. | Need to check tomorrow on BNF | Need to Fix | Not Resolved | Only Selected Strike only Showing the price
005 - Bottom Tabs | Bug | The search box in the watch list is not working; typing the first 4-5 letters should show nearest instrument names. | Yes | Need to Fix | Not Resolved | Not able to optionstrikes
005 - Bottom Tabs | Limitation | Items can only be added to the watch list from the option chain. | Yes | Need to Fix | Not Resolved
005 - Bottom Tabs | Working | The Option Chain is working without general visual problems. | Yes | Need to Fix | Not Resolved | Only Selected Strike only Showing the price
005 - Bottom Tabs | Working | Adding a watch list and creating folders is working. | Yes | No Problem | Resolved

## QA Report_02
| Description | Action Required | Status | Error
1 | The profile page needs optimization; some data is cut off at the bottom of the screen. | Need to Fix | Not Resolved | some data cut-off bottom of the screen
2 | The "Margin ReQ" information being pulled is wrong. | Need to Fix | Partial Resolved | Not Pulling correctly. For Sell orders & Futures it's not showing correctly. Need to Research on Fyers and take reference of Fyers Margin Calculator
3 | A Market depth window is needed for limit order price assumptions. | Need to Fix | Not Resolved | Failing to load
4 | Option chain live data is not updating for strike prices. | Need to Fix | Not Resolved | Only Selected Strike only Showing the price
5 | The search box in the watch list is not working; typing the first 4-5 letters should show nearest instrument names. | Need to Fix | Not Resolved | Search box is working But it's loading Instrument Futures only.Not able to add BNF optionstrikes. Also Not Showing NIFTY and Sensex
New Issue
7 | in Order Placement window, After Refresh, BNF Futures Loading automatically BUT besides Showing Chart Selected Option Price.
8 | For Same Option Strike, After Placing the BUY order, There Should be "Sell" Button Instead of "Exit" already BUY Position is there then If I place Sell Order, it should close the existing BUY Position.
9 | Place order and positions should be in the same window, like a dropdown. |  |  | Not Properly Fitted. Ongoing P-L is not visible in window.
10 | Closed Positions should be shown in Positions with P & L in Grey colour. Total list will be reset after 11:55 PM every day ( end of the Day )
11 | Partial Exit Issue : For Example, If lot Size is 30, in Partial exit, now, I am able select 5 Qty and have option to exit 5Qty. It's wrong. With in lot qty, cannot to be exit. If position has more than 1 lot, then lot qty can only be exit.
12 | Specific Instruments Only Showing in main search bar( header ) it should show all the instruments which fyers can show.